## Overview
Overview
This document includes the following tabs to help you plan a quality speech contest.
| For additional resources, go to: | http://d37toastmasters.org/speech-contests/
Project Plan:
List of tasks to be completed and timeline. Enter your contest date in the first row to populate due dates for each task.
Contest Day Checklist:
Use this as a guide to keep track of tasks that must be completed on contest day. Enter your contest start time in the first row.
Participants:
Enter contact information to easily track who has arrived on contest day, and how to reach key participants quickly if needed.
Forms:
List of all forms that must be available at a speech contest.
Materials:
List of physical materials to bring to a speech contest.

## Project Plan
Project Plan | ENTER CONTEST DATE IN CELL C1: | 2019-02-27
Task | Owner | Due Date |  | Weeks | Done? | Comments
Appoint Contest Chair | District Leader/VPE | 2019-01-16 | 42 | 6
Schedule Date and Time | Contest Chair | 2019-01-16 | 42 | 6
Secure Location | Contest Chair | 2019-01-16 | 42 | 6
Form a committee, review tasks in this plan and delegate ownership of tasks | Contest Chair | 2019-01-16 | 42 | 6
Add event to District Calendar | Contest Chair | 2019-01-16 | 42 | 6
Publicize contest and call for contestants | Contest Chair | 2019-01-16 | 42 | 6
Review Speech Contest Resources on District Website | Contest Chair | 2019-01-23 | 35 | 5
Select Contest Master | Contest Chair | 2019-01-23 | 35 | 5
Select Chief Judge | Contest Chair | 2019-01-23 | 35 | 5
Select Sergeant-At-Arms | Contest Chair | 2019-01-23 | 35 | 5
Select Refreshments Owner | Contest Chair | 2019-01-23 | 35 | 5
Select Awards Owner | Contest Chair | 2019-01-23 | 35 | 5
Meet with Contest Master to review contestant briefing and clarify task owners | Contest Chair | 2019-01-30 | 28 | 4
Meet with Chief Judge to review judges briefing and clarify task owners | Contest Chair | 2019-01-30 | 28 | 4
Meet with Refreshments Owner to review budget | Contest Chair | 2019-01-30 | 28 | 4
Meet with Awards Owner to plan for trophies and certificates | Contest Chair | 2019-01-30 | 28 | 4
Invite district leaders and Toastmasters from other clubs | Contest Chair | 2019-01-30 | 28 | 4
Read Speech Contest Rulebook | Contest Chair | 2019-02-02 12:00 | 24.5 | 3.5
Select Test Speaker (Evaluation Contest only) | Contest Chair | 2019-02-06 | 21 | 3
Select Sergeant-at-Arms assistants | Contest Chair | 2019-02-06 | 21 | 3
Select Judges | Chief Judge | 2019-02-06 | 21 | 3
Select Ballot Counters | Chief Judge | 2019-02-06 | 21 | 3
Select Timers | Chief Judge | 2019-02-06 | 21 | 3
Review list of forms and confirm with team who will bring each to contest | Contest Chair | 2019-02-09 12:00 | 17.5 | 2.5
Review list of materials, delegate and ensure they will be at the contest | Contest Chair | 2019-02-09 12:00 | 17.5 | 2.5
Confirm list of contestants and backup contestants | Contest Chair | 2019-02-13 | 14 | 2
Send rulebook, eligibility and profile forms to contestants | Contest Chair | 2019-02-13 | 14 | 2
Send rulebook, judge certification of eligibility form to judges | Contest Chair | 2019-02-13 | 14 | 2
Confirm contestant eligibility | Contest Chair | 2019-02-13 | 14 | 2
Confirm judge eligibility | Chief Judge | 2019-02-13 | 14 | 2
Print certificates | Awards Owner | 2019-02-13 | 14 | 2
Ensure all contest participants know to arrive at least 30 minutes early | Contest Chair | 2019-02-13 | 14 | 2
Plan the day-of-contest briefing for contestants | Contest Master | 2019-02-13 | 14 | 2
Plan the day-of-contest briefing for judges, timers and counters | Chief Judge | 2019-02-13 | 14 | 2
Schedule call with contestants to share details and answer questions | Contest Chair | 2019-02-13 | 14 | 2
Schedule call with judges to share details and answer questions | Contest Chair | 2019-02-13 | 14 | 2
Complete Participants list for use on contest day (in this workbook) | Contest Chair | 2019-02-16 12:00 | 10.5 | 1.5
Review Contest Day Checklist, delegate tasks, adjust times as needed | Contest Chair | 2019-02-20 | 7 | 1
Touch base with Refreshments Owner and address any issues | Contest Chair | 2019-02-20 | 7 | 1
Touch base with Awards Owner and address any issues | Contest Chair | 2019-02-20 | 7 | 1
For Table Topics contests, give the question to the Contest Master | Contest Chair | 2019-02-20 | 7 | 1
Review and personalize contest scripts | Contest Master | 2019-02-20 | 7 | 1
Create and print contest agendas | Contest Chair | 2019-02-20 | 7 | 1
Prepare extra copies of forms to bring on contest day | Contest Chair | 2019-02-20 | 7 | 1
Prepare folder for each judge (eligibility form and ballots) | Chief Judge | 2019-02-20 | 7 | 1
Prepare folder for tiebreaker judge (eligibility form and ballots) | Chief Judge | 2019-02-20 | 7 | 1
Personalize certificates | Awards Owner | 2019-02-20 | 7 | 1
Send e-mail reminder to Contestants | Contest Chair | 2019-02-23 12:00 | 3.5 | 0.5
Send e-mail reminder to Contest Officials | Chief Judge | 2019-02-23 12:00 | 3.5 | 0.5
Select and brief the tie-breaking judge | Chief Judge | 2019-02-23 12:00 | 3.5 | 0.5
Provide introduction to the Sergeant-at-Arms | Contest Master | 2019-02-23 12:00 | 3.5 | 0.5
Make list of people to thank/recognize after contest | Contest Chair | 2019-02-23 12:00 | 3.5 | 0.5
Forward contestant eligibility and profile forms to Contest Master | Contest Chair | 2019-02-25 06:00 | 1.75 | 0.25
Confirm contest day arrival times with key participants | Contest Chair | 2019-02-25 06:00 | 1.75 | 0.25
Smile. Breathe. | Contest Chair | 2019-02-27 | 0 | 0
Use "Contest Day Checklist" to lead a successful contest | Contest Chair | 2019-02-27 | 0 | 0
Submit contest result forms to next-level contest chair | Contest Chair | 2019-03-02 12:00 | -3.5 | -0.5
Write Thank-Yous to your team | Contest Chair | 2019-03-02 12:00 | -3.5 | -0.5
Write Thank-Yous to contest officials | Chief Judge | 2019-03-02 12:00 | -3.5 | -0.5
Celebrate leading a well planned, organized, and executed contest! | Contest Chair | 2019-03-02 12:00 | -3.5 | -0.5

## Contest Day Checklist
Contest Day Checklist | ENTER CONTEST TIME IN CELL C1: | 19:00
| Owner | Due Date | Before/After | Done? | Comments
Arrive at contest location | Contest Chair | 18:00 | 1:00
Determine location for contestant briefings | Contest Chair | 18:10 | 0:50
Determine location for judges/timers/counters briefings | Contest Chair | 18:10 | 0:50
Confirm arrival of each participant (see Participants tab in this document) | Contest Chair | 18:15 | 0:45
Give forms and folders to Chief Judge | Contest Chair | 18:15 | 0:45
Bring refreshments | Refreshments Owner | 18:15 | 0:45
Define speaking area | Contest Chair | 18:25 | 0:35
Define location of timing lights | Contest Chair | 18:25 | 0:35
Define staging area for contestants to wait during moment of silence | Contest Chair | 18:25 | 0:35
Define holding area for Table Topics/Evaluation contestants | Sergeant-at-Arms | 18:25 | 0:35
Ensure that contestants in holding area will not be able to hear contest | Sergeant-at-Arms | 18:25 | 0:35
Post “Contest In Progress” signs on the contest room doors | Sergeant-at-Arms | 18:25 | 0:35
Conduct Contestant Briefing | Contest Chair | 18:30 | 0:30
Conduct Judges/Timers/Counters Briefing | Chief Judge | 18:30 | 0:30
Conduct Sergeant-at-Arms Briefing | Sergeant-at-Arms | 18:30 | 0:30
Confirm that forms have been received from all contestants | Chief Judge | 18:45 | 0:15
Confirm that forms have been received from all judges | Chief Judge | 18:45 | 0:15
Find role replacements, if necessary | Contest Chair | 18:45 | 0:15
Check with the Contest Master to see if any contestants need help with props | Sergeant-at-Arms | 18:45 | 0:15
Announce that the Speech Contest will be called to order in five minutes | Sergeant-at-Arms | 18:55 | 0:05
Call the Speech Contest to order | Sergeant-at-Arms | 19:00 | 0:00
Watch your team succeed and be available for help if needed! | Contest Chair | 19:00 | 0:00

## Participants
Participants
Role | Name | Phone | E-mail | Arrived? | Comments
Contest Chair
Contest Master
Chief Judge
Awards Owner
Refreshments Owner
Test Speaker (Evaluation only)
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Tie-Breaker Judge
Ballot Counter
Ballot Counter
Ballot Counter
Timer
Timer
Sergeant-at-Arms (Lead)
Sergeant-at-Arms (Assistant)
Sergeant-at-Arms (Assistant)
Utility Player (can fill any role)
Utility Player (can fill any role)
Utility Player (can fill any role)
Contest 1 | Name | Phone |  | Arrived? | Comments
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contest 2 | Name | Phone |  | Arrived? | Comments
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant

## Forms
Forms
The following is a guide to which forms are required at a speech contest. Filter by Owner to determine who is responsible for each form, and also by Contest Type.
All forms can be downloaded at http://d37toastmasters.org/speech-contests/
Number | Name | International | Table Topics | Humorous | Evaluation | Owner | Comments
1168 | Results Form | X | X | X | X | Chief Judge | give to Contest Master before announcement of winners
1170 | Judge's Certification of Eligibility | X | X | X | X | Judges | give to Chief Judge before contest begins
1171 | Speech Contest Rulebook | X | X | X | X | Contest Chair | for reference
1172 | International Speech Contest - Judge's Guide and Ballot | X |  |  |  | Judges | give ballot to Counters after voting, shred remainder after contest
1175 | Time Record Sheet | X | X | X | X | Chief Judge | collect from Timers before counting ballots
1176 | Counters Tally Sheet | X | X | X | X | Chief Judge | collect from Counters before counting ballots
1182 | Notification of Contest Winner | X | X | X | X | Contest Chair | give to next-level Contest Chair after announcement of winners
1183 | Speaker's Certification of Eligibility and Originality | X | X | X | X | Contestants | give to Contest Master at briefing
1188 | International Speech Contest - Tiebreaker Judge's Guide and Ballot | X |  |  |  | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
1189 | Speech Contestant Profile | X | X | X | X | Contestants | give to Contest Master at briefing
1193 | International Speech Contest - Video Release Form (District Contest only) | X |  |  |  | Contestants | give to Contest Master at briefing
1180 | Table Topics Contest - Judge's Guide and Ballot |  | X |  |  | Judges | give ballot to Counters after voting, shred remainder after contest
1180A | Table Topics Contest - Tiebreaker Judge's Guide and Ballot |  | X |  |  | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
1177 | Evaluation Contestant Notes |  |  |  | X | Contestants | for use in preparation area before speech
1179 | Evaluation Contest - Judge's Guide and Ballot |  |  |  | X | Judges | give ballot to Counters after voting, shred remainder after contest
1179A | Evaluation Contest - Tiebreaker Judge's Guide and Ballot |  |  |  | X | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
1191 | Humorous Speech Contest - Judge's Guide and Ballot |  |  | X |  | Judges | give ballot to Counters after voting, shred remainder after contest
1191A | Humorous Speech Contest - Tiebreaker Judge's Guide and Ballot |  |  | X |  | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
510A | Speech Contest First Place Certificate | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners
510B | Speech Contest Second Place Certificate | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners
510C | Speech Contest Third Place Certificate | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners
510D | Speech Contest Certificate of Participation | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners

## Materials
Materials
Item | Owner | Done? | Comments
Food | Refreshments Owner
Beverages | Refreshments Owner
Trophies | Awards Owner
Certificates | Awards Owner
Pens | Contest Chair
Timing Indictors (minimum of 2) | Contest Chair
Stopwatches (minimum of 2) | Contest Chair
Playing cards (to draw for order) | Contest Chair
Envelopes | Contest Chair
Lectern | Contest Chair
Gavel | Contest Chair
Club Banners | Contest Chair
Flag | Contest Chair
Contest Master Scripts | Contest Chair
Contestant Briefing Script | Contest Chair
Judges Briefing Script | Contest Chair
Sergeant-At-Arms Briefing Script | Contest Chair
Folders for judges | Contest Chair
Folder for tiebreaker judge | Contest Chair
Extra forms | Contest Chair
“Contest In Progress” signs for doors | Sergeant-at-Arms