## Overview
Overview
This document includes the following tabs to help you plan a quality speech contest.
| For additional resources, go to: | http://d37toastmasters.org/speech-contests/
Project Plan:
List of tasks to be completed and timeline. Enter your contest date in the first row to populate due dates for each task.
Contest Day Checklist:
Use this as a guide to keep track of tasks that must be completed on contest day. Enter your contest start time in the first row.
Participants:
Enter contact information to easily track who has arrived on contest day, and how to reach key participants quickly if needed.
Forms:
List of all forms that must be available at a speech contest.
Materials:
List of physical materials to bring to a speech contest.
Dignitaries:
List of dignitaries in attendance, to be completed on the day of the contest and given to the Contest Master.

## Project Plan
Project Plan | ENTER CONTEST DATE IN CELL C1: | 2019-02-27
Task | Owner | Due Date |  | Weeks | Done? | Comments
Appoint Contest Chair | District Leader/VPE | 2019-01-16 | 42 | 6
Schedule Date and Time | Contest Chair | 2019-01-16 | 42 | 6
Secure Location | Contest Chair | 2019-01-16 | 42 | 6
Form a committee, review tasks in this plan and delegate ownership of tasks | Contest Chair | 2019-01-16 | 42 | 6
Add event to District Calendar | Contest Chair | 2019-01-16 | 42 | 6
Publicize contest and call for contestants | Contest Chair | 2019-01-16 | 42 | 6
Review Speech Contest Resources on District Website | Contest Chair | 2019-01-23 | 35 | 5
Select Contest Master | Contest Chair | 2019-01-23 | 35 | 5
Select Chief Judge | Contest Chair | 2019-01-23 | 35 | 5
Select Sergeant-At-Arms | Contest Chair | 2019-01-23 | 35 | 5
Select Refreshments Owner | Contest Chair | 2019-01-23 | 35 | 5
Select Awards Owner | Contest Chair | 2019-01-23 | 35 | 5
Meet with Contest Master to review contestant briefing and clarify task owners | Contest Chair | 2019-01-30 | 28 | 4
Meet with Chief Judge to review judges briefing and clarify task owners | Contest Chair | 2019-01-30 | 28 | 4
Meet with Refreshments Owner to review budget | Contest Chair | 2019-01-30 | 28 | 4
Meet with Awards Owner to plan for trophies and certificates | Contest Chair | 2019-01-30 | 28 | 4
Invite district leaders and Toastmasters from other clubs | Contest Chair | 2019-01-30 | 28 | 4
Read Speech Contest Rulebook | Contest Chair | 2019-02-02 12:00 | 24.5 | 3.5
Select Test Speaker (Evaluation Contest only) | Contest Chair | 2019-02-06 | 21 | 3
Select Sergeant-at-Arms assistants | Contest Chair | 2019-02-06 | 21 | 3
Select Judges (see Section 5-A of Speech Contest Rulebook) | Chief Judge | 2019-02-06 | 21 | 3
Select Ballot Counters | Chief Judge | 2019-02-06 | 21 | 3
Select Timers | Chief Judge | 2019-02-06 | 21 | 3
Instruct all Judges, Ballot Counters and Timers to view the TI tutorials | Chief Judge | 2019-02-06 | 21 | 3
Review list of forms and confirm with team who will bring each to contest | Contest Chair | 2019-02-09 12:00 | 17.5 | 2.5
Review list of materials, delegate and ensure they will be at the contest | Contest Chair | 2019-02-09 12:00 | 17.5 | 2.5
Confirm list of contestants and backup contestants | Contest Chair | 2019-02-13 | 14 | 2
Send rulebook, eligibility and profile forms to contestants | Contest Chair | 2019-02-13 | 14 | 2
Send rulebook, judge certification of eligibility form to judges | Contest Chair | 2019-02-13 | 14 | 2
Confirm contestant eligibility | Contest Chair | 2019-02-13 | 14 | 2
Confirm judge eligibility (see Section 2-B of Speech Contest Rulebook) | Chief Judge | 2019-02-13 | 14 | 2
Print certificates | Awards Owner | 2019-02-13 | 14 | 2
Ensure all contest participants know to arrive at least 30 minutes early | Contest Chair | 2019-02-13 | 14 | 2
Plan the day-of-contest briefing for contestants | Contest Master | 2019-02-13 | 14 | 2
Plan the day-of-contest briefing for judges, timers and counters | Chief Judge | 2019-02-13 | 14 | 2
Schedule call with contestants to share details and answer questions | Contest Chair | 2019-02-13 | 14 | 2
Schedule call with judges to share details and answer questions | Contest Chair | 2019-02-13 | 14 | 2
Complete Participants list for use on contest day (in this workbook) | Contest Chair | 2019-02-16 12:00 | 10.5 | 1.5
Replace any judges that share club membership with a contestant | Chief Judge | 2019-02-20 | 7 | 1
Review Contest Day Checklist, delegate tasks, adjust times as needed | Contest Chair | 2019-02-20 | 7 | 1
Touch base with Refreshments Owner and address any issues | Contest Chair | 2019-02-20 | 7 | 1
Touch base with Awards Owner and address any issues | Contest Chair | 2019-02-20 | 7 | 1
For Table Topics contests, give the question to the Contest Master | Contest Chair | 2019-02-20 | 7 | 1
Review and personalize contest scripts | Contest Master | 2019-02-20 | 7 | 1
Create and print contest agendas | Contest Chair | 2019-02-20 | 7 | 1
Prepare extra copies of forms to bring on contest day | Contest Chair | 2019-02-20 | 7 | 1
Prepare folder for each judge (eligibility form and ballots) | Chief Judge | 2019-02-20 | 7 | 1
Prepare folder for tiebreaker judge (eligibility form and ballots) | Chief Judge | 2019-02-20 | 7 | 1
Personalize certificates | Awards Owner | 2019-02-20 | 7 | 1
Send e-mail reminder to Contestants | Contest Chair | 2019-02-23 12:00 | 3.5 | 0.5
Send e-mail reminder to Contest Officials | Chief Judge | 2019-02-23 12:00 | 3.5 | 0.5
Select and brief the tie-breaking judge | Chief Judge | 2019-02-23 12:00 | 3.5 | 0.5
Provide introduction to the Sergeant-at-Arms | Contest Master | 2019-02-23 12:00 | 3.5 | 0.5
Make list of people to thank/recognize after contest | Contest Chair | 2019-02-23 12:00 | 3.5 | 0.5
Forward contestant eligibility and profile forms to Contest Master | Contest Chair | 2019-02-25 06:00 | 1.75 | 0.25
Confirm contest day arrival times with key participants | Contest Chair | 2019-02-25 06:00 | 1.75 | 0.25
Smile. Breathe. | Contest Chair | 2019-02-27 | 0 | 0
Use "Contest Day Checklist" to lead a successful contest | Contest Chair | 2019-02-27 | 0 | 0
Submit contest result forms to next-level contest chair | Contest Chair | 2019-03-02 12:00 | -3.5 | -0.5
Write Thank-Yous to your team | Contest Chair | 2019-03-02 12:00 | -3.5 | -0.5
Write Thank-Yous to contest officials | Chief Judge | 2019-03-02 12:00 | -3.5 | -0.5
Celebrate leading a well planned, organized, and executed contest! | Contest Chair | 2019-03-02 12:00 | -3.5 | -0.5

## Contest Day Checklist
Contest Day Checklist | ENTER CONTEST TIME IN CELL C1: | 19:00
| Owner | Due Date | Before/After | Done? | Comments
Arrive at contest location | Contest Chair | 18:00 | 1:00
Place signs outside to direct guests to the contest location | Sergeant-at-Arms | 18:05 | 0:55
Determine location for contestant briefings | Contest Chair | 18:10 | 0:50
Determine location for judges/timers/counters briefings | Contest Chair | 18:10 | 0:50
Set aside the first row in the audience for contestant seating | Contest Chair | 18:10 | 0:50
Confirm arrival of each participant (see Participants tab in this document) | Contest Chair | 18:15 | 0:45
Give forms and folders to Chief Judge | Contest Chair | 18:15 | 0:45
Bring refreshments | Refreshments Owner | 18:15 | 0:45
Define speaking area | Contest Chair | 18:25 | 0:35
Define location of timing lights | Contest Chair | 18:25 | 0:35
Define staging area for contestants to wait during moment of silence | Contest Chair | 18:25 | 0:35
Define holding area for Table Topics/Evaluation contestants | Sergeant-at-Arms | 18:25 | 0:35
Ensure that contestants in holding area will not be able to hear contest | Sergeant-at-Arms | 18:25 | 0:35
Post “Contest In Progress” signs on the contest room doors | Sergeant-at-Arms | 18:25 | 0:35
Conduct Contestant Briefing | Contest Chair | 18:30 | 0:30
Conduct Judges/Timers/Counters Briefing | Chief Judge | 18:30 | 0:30
Conduct Sergeant-at-Arms Briefing | Sergeant-at-Arms | 18:30 | 0:30
Complete a list of the dignitaries in attendance for the Contest Master | Contest Chair | 18:40 | 0:20
Confirm that forms have been received from all contestants | Chief Judge | 18:45 | 0:15
Confirm that forms have been received from all judges | Chief Judge | 18:45 | 0:15
Find role replacements, if necessary | Contest Chair | 18:45 | 0:15
Check with the Contest Master to see if any contestants need help with props | Sergeant-at-Arms | 18:45 | 0:15
Announce that the Speech Contest will be called to order in five minutes | Sergeant-at-Arms | 18:55 | 0:05
Call the Speech Contest to order | Sergeant-at-Arms | 19:00 | 0:00
Watch your team succeed and be available for help if needed! | Contest Chair | 19:00 | 0:00

## Participants
Participants
Role | Name | Phone | E-mail | Arrived? | Comments
Contest Chair
Contest Master
Chief Judge
Awards Owner
Refreshments Owner
Test Speaker (Evaluation only)
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Judge
Tie-Breaker Judge
Ballot Counter
Ballot Counter
Ballot Counter
Timer
Timer
Sergeant-at-Arms (Lead)
Sergeant-at-Arms (Assistant)
Sergeant-at-Arms (Assistant)
Utility Player (can fill any role)
Utility Player (can fill any role)
Utility Player (can fill any role)
Contest 1 | Name | Phone |  | Arrived? | Comments
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contest 2 | Name | Phone |  | Arrived? | Comments
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant

## Forms
Forms
The following is a guide to which forms are required at a speech contest. Filter by Owner to determine who is responsible for each form, and also by Contest Type.
All forms can be downloaded at http://d37toastmasters.org/speech-contests/
Number | Name | International | Table Topics | Humorous | Evaluation | Owner | Comments
1168 | Results Form | X | X | X | X | Chief Judge | give to Contest Master before announcement of winners
1170 | Judge's Certification of Eligibility | X | X | X | X | Judges | give to Chief Judge before contest begins
1171 | Speech Contest Rulebook | X | X | X | X | Contest Chair | for reference
1172 | International Speech Contest - Judge's Guide and Ballot | X |  |  |  | Judges | give ballot to Counters after voting, shred remainder after contest
1175 | Time Record Sheet | X | X | X | X | Chief Judge | collect from Timers before counting ballots
1176 | Counters Tally Sheet | X | X | X | X | Chief Judge | collect from Counters before counting ballots
1182 | Notification of Contest Winner | X | X | X | X | Contest Chair | give to next-level Contest Chair after announcement of winners
1183 | Speaker's Certification of Eligibility and Originality | X | X | X | X | Contestants | give to Contest Master at briefing
1188 | International Speech Contest - Tiebreaker Judge's Guide and Ballot | X |  |  |  | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
1189 | Speech Contestant Profile | X | X | X | X | Contestants | give to Contest Master at briefing
1193 | International Speech Contest - Video Release Form (District Contest only) | X |  |  |  | Contestants | give to Contest Master at briefing
1180 | Table Topics Contest - Judge's Guide and Ballot |  | X |  |  | Judges | give ballot to Counters after voting, shred remainder after contest
1180A | Table Topics Contest - Tiebreaker Judge's Guide and Ballot |  | X |  |  | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
1177 | Evaluation Contestant Notes |  |  |  | X | Contestants | for use in preparation area before speech
1179 | Evaluation Contest - Judge's Guide and Ballot |  |  |  | X | Judges | give ballot to Counters after voting, shred remainder after contest
1179A | Evaluation Contest - Tiebreaker Judge's Guide and Ballot |  |  |  | X | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
1191 | Humorous Speech Contest - Judge's Guide and Ballot |  |  | X |  | Judges | give ballot to Counters after voting, shred remainder after contest
1191A | Humorous Speech Contest - Tiebreaker Judge's Guide and Ballot |  |  | X |  | Tiebreaker Judge | give ballot to Chief Judge after voting, shred remainder after contest
510A | Speech Contest First Place Certificate | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners
510B | Speech Contest Second Place Certificate | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners
510C | Speech Contest Third Place Certificate | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners
510D | Speech Contest Certificate of Participation | X | X | X | X | Awards Owner | give to Contest Master before announcement of winners

## Materials
Materials
Item | Owner | Done? | Comments
Food | Refreshments Owner
Beverages | Refreshments Owner
Trophies | Awards Owner
Certificates | Awards Owner
Outdoor signs to direct guests to location | Sergeant-at-Arms
“Contest In Progress” signs for doors | Sergeant-at-Arms
Pens | Contest Chair
Timing Indicators (minimum of 2) | Contest Chair
Stopwatches (minimum of 2) | Contest Chair
Playing cards (to draw for order) | Contest Chair
Envelopes | Contest Chair
Lectern | Contest Chair
Gavel | Contest Chair
Club Banners | Contest Chair
Flag | Contest Chair
Contest Master Scripts | Contest Chair
Contestant Briefing Script | Contest Chair
Judges Briefing Script | Contest Chair
Sergeant-At-Arms Briefing Script | Contest Chair
Folders for judges | Contest Chair
Folder for tiebreaker judge | Contest Chair
Extra forms | Contest Chair

## Dignitaries
Dignitaries
Role | Name
District Director
Program Quality Director
Club Growth Director
Club Growth Director
Past District Director
Past District Director
Past District Director
Past District Director
Division Director
Division Director
Division Director
Area Director
Area Director
Area Director
Area Director
Area Director
Area Director
Area Director
Area Director
Area Director
Area Director